SCOPE MANAGEMENT DOCUMENT

Aigentic AI — Automated Inbox Alert Triage & Remediation

D&A DLC Notifications | Phased Implementation | Funding Approval Request

| Document Owner | D&A DLC Platform Team |
| --- | --- |
| Version | v1.0 — Initial Scope |
| Status | Pending Funding Approval |
| Classification | Confidential — Internal |
| Date | March 11, 2026 |
| Target Audience | Engineering Leadership, FinOps, Security & Compliance |

# 1. Executive Summary

The D&A DLC Notifications mailbox currently receives thousands of automated alerts spanning AWS infrastructure, security, compliance, and operational health. These alerts arrive across multiple categories — Production Alerts, Corrective Actions, Cost Reports, and more — with no automated severity classification, prioritization, or remediation workflow.

This document defines the scope and phased implementation plan for an Aigentic AI solution that will: (1) segregate alerts by environment, (2) classify them by severity, (3) auto-remediate safe Critical alerts with zero production impact, and (4) auto-close resolved incidents — reducing toil, improving MTTR, and freeing engineering capacity.

# 2. Problem Statement

## 2.1 Current State — Alert Volume

The following alert volumes are observed in the current mailbox (as of scope baseline):

| Category | Alert / Folder | Current Volume | Environment |
| --- | --- | --- | --- |
| Inbox | General Inbox | 477 | Mixed |
| Inbox | AWS Notifications | 9 | Mixed |
| Inbox | AWS Case Tickets | 482 | Mixed |
| Production | ServiceQuota Alerts | 142 | Production |
| Production | Cactus Corrective Action | 203 | Production |
| Production | Non-Compliance | 66 | Production |
| Production | Unauthorised API Calls | 481 | Production |
| Production | GuardDuty Alerts | 63 | Production |
| Production | KMS Data Perimeter | — | Production |
| Production | SQS Alerts | — | Production |
| Production | S3 Data Perimeter | — | Production |
| Corrective | Corrective Actions (total) | 1002 | Mixed |
| Corrective | cactus_kms_data_perimeter | 844 | Mixed |
| Corrective | cactus_s3_data_perimeter | 6447 | Mixed |
| Corrective | cactus_sqs_data_perimeter | 157 | Mixed |
| Corrective | CISBenchmark | 2601 | Mixed |
| Corrective | Health Reports | 423 | Mixed |
| Corrective | Guard Duty Alerts | 1032 | Mixed |
| Corrective | Non-Compliance Reports | 4242 | Mixed |
| Corrective | UnauthorizedAPICalls | 1566 | Mixed |
| Corrective | EMR Version | — | Mixed |
| Corrective | Service Quota | 104 | Mixed |
| Cost | DAILY COST REPORT | 1375 | All |

## 2.2 Key Gaps in Current State

- No severity classification — alerts do not indicate Critical / High / Medium / Low

- No environment segregation — Production and Non-Production alerts are mixed

- No auto-remediation — engineers manually investigate every alert

- No incident auto-closure — resolved issues remain open, inflating noise

- Engineer toil — thousands of alerts reviewed manually daily

- Risk of missed Critical alerts due to volume and fatigue

# 3. Objectives

- Automatically segregate alerts into Production vs. Non-Production streams

- Classify every alert with a severity level: Critical / High / Medium / Low

- Auto-remediate Critical alerts that are safe and non-impactful to production

- Auto-close incidents once resolution is confirmed

- Reduce manual engineer toil and mean time to resolution (MTTR)

- Provide a real-time dashboard for alert health and SLA tracking

# 4. Scope of Work

## 4.1 In Scope

- All alert categories in D&A DLC Notifications mailbox

- Production Alerts: ServiceQuota, Cactus Corrective Action, Non-Compliance, Unauthorised API Calls, GuardDuty, KMS, SQS, S3 Data Perimeter

- Corrective Actions: cactus_kms/s3/sqs_data_perimeter, CISBenchmark, Health Reports, GuardDuty, Non-Compliance, UnauthorizedAPICalls, EMR Version, Service Quota

- Cost Reporting: DAILY COST REPORT (1375 alerts)

- AWS Notifications and AWS Case Tickets

- Severity tagging engine (Critical / High / Medium / Low)

- Auto-remediation playbooks for non-impactful Critical alerts

- Incident auto-closure workflows

- Monitoring dashboard and weekly summary digest

## 4.2 Out of Scope

- Manual remediation of High / Medium / Low alerts in Phase 1

- Changes to upstream AWS alert configurations

- Third-party ticketing system integrations (future phase)

- Non-AWS alert sources

# 5. Phased Implementation Plan

## Phase 1 — Environment Segregation & Ingestion Pipeline

Objective: Build the foundational ingestion and routing layer that separates Production from Non-Production alerts.

| Activity | Description | Timeline |
| --- | --- | --- |
| Alert Ingestion | Connect mailbox to Aigentic AI pipeline via email parsing or API hook | Week 1–2 |
| Environment Classification | Tag each alert as Production or Non-Production using account/tag metadata | Week 2–3 |
| Routing Rules | Route alerts to separate queues; apply folder/label rules automatically | Week 3–4 |
| Baseline Metrics | Capture pre-automation volumes per category as baseline KPIs | Week 4 |

Phase 1 Deliverables:

- Segregated Production and Non-Production alert streams

- Ingestion pipeline operational and logging all events

- Baseline alert volume dashboard

## Phase 2 — Severity Classification Engine

Objective: Enrich every alert with a severity label (Critical / High / Medium / Low) using AI-driven classification rules.

| Severity | Alert Types | Classification Criteria | SLA Target |
| --- | --- | --- | --- |
| CRITICAL | GuardDuty, Unauthorised API, Non-Compliance | Active threat, data exfiltration risk, security boundary breach | 15 minutes |
| HIGH | ServiceQuota, CISBenchmark, KMS | Service degradation risk, quota breach imminent, policy violation | 1 hour |
| MEDIUM | Health Reports, EMR Version, SQS | Operational advisory, version drift, non-urgent compliance gap | 4 hours |
| LOW | Daily Cost Reports, S3 Perimeter, Cactus CA | Informational, trend monitoring, no immediate action needed | 24 hours |

Phase 2 Deliverables:

- AI severity classification model trained on historical alert patterns

- Real-time severity tagging on all incoming alerts

- Severity-based alerting channels (PagerDuty / Slack / Email)

- Weekly severity distribution report

## Phase 3 — Auto-Remediation of Non-Impactful Critical Alerts

Objective: For Critical alerts that are safe to remediate without production impact, execute automated fix playbooks and close the incident.

### Auto-Remediation Playbooks — Initial Set

| Alert Type | Auto-Remediation Action | Impact Assessment | Auto-Close? |
| --- | --- | --- | --- |
| cactus_kms_data_perimeter (844) | Re-apply KMS key policy to enforce data perimeter boundary | Zero Impact | Yes |
| cactus_s3_data_perimeter (6447) | Enforce S3 bucket policy; block public access if misconfigured | Zero Impact | Yes |
| cactus_sqs_data_perimeter (157) | Re-apply SQS queue policy to restrict to VPC endpoints only | Zero Impact | Yes |
| UnauthorizedAPICalls (1566) | Isolate IAM principal; revoke temp credentials; trigger investigation | Low Impact | Conditional |
| ServiceQuota Near-Breach | Submit automated quota increase request via AWS API | Zero Impact | Yes |
| EMR Version Drift | Flag for patching window; create JIRA ticket automatically | Zero Impact | No — Track |
| CISBenchmark Violation (2601) | Apply compliant config via SSM / Config Rules remediation | Low Impact | Yes |

Phase 3 Deliverables:

- Automated remediation playbooks for 7+ alert types

- Human-in-the-loop approval gate for borderline cases

- Incident auto-closure with audit trail and evidence snapshot

- Estimated alert reduction: ~70% of current volume auto-resolved

## Phase 4 — Observability, Reporting & Continuous Improvement

Objective: Provide full visibility into alert health, SLA compliance, and AI model accuracy. Continuously improve classification and remediation.

- Real-time dashboard: alert volumes, severity breakdown, auto-close rates

- Weekly digest email replacing individual alert floods

- Monthly AI model retraining on false-positive feedback

- SLA breach alerting for Critical alerts exceeding 15-minute response

- Cost savings report tied to engineer hours saved

# 6. Success Metrics & KPIs

| KPI | Current Baseline | Phase 2 Target | Phase 3 Target |
| --- | --- | --- | --- |
| Alert auto-classification rate | 0% (manual) | 90%+ | 95%+ |
| Critical alert MTTR | >4 hours (manual) | <1 hour | <15 min |
| Alert auto-close rate | 0% | N/A | 60–70% |
| False positive rate | Unknown | <10% | <5% |
| Engineer hours saved per week | 0 (baseline) | ~5 hrs/week | ~20 hrs/week |

# 7. Risks & Mitigations

| # | Risk | Likelihood | Mitigation | Owner |
| --- | --- | --- | --- | --- |
| 1 | AI misclassifies Critical alert as Low | Medium | Human review gate on all auto-remediations; weekly model retraining | AI/ML Engineer |
| 2 | Auto-remediation causes unintended config change | Low | Dry-run mode in Phase 3; blast radius limited to non-impactful playbooks only | Platform Lead |
| 3 | Alert schema changes break ingestion pipeline | Medium | Schema versioning; automated schema validation on ingestion | Data Engineer |
| 4 | Scope creep delays Phase 1 delivery | High | Strict phase gates; change control board approval required for additions | Project Manager |

# 8. Funding Request

## 8.1 Cost Estimate Summary

| Cost Item | Phase | Est. Cost (USD) | Type |
| --- | --- | --- | --- |
| AI/ML Engineer (6 months) | Phase 1–3 | $60,000 | CapEx |
| Platform / DevOps Engineer (4 months) | Phase 1–2 | $36,000 | CapEx |
| AI Model Hosting & Inference (annual) | Phase 2+ | $12,000 | OpEx |
| Dashboard & Observability Tooling | Phase 4 | $8,000 | CapEx |
| Testing, QA & Security Review | All Phases | $10,000 | CapEx |
| TOTAL ESTIMATED INVESTMENT |  | $126,000 | Year 1 |

## 8.2 Return on Investment

- ~20 engineer hours/week saved at Phase 3 completion → ~$80,000/year in productivity

- Faster Critical alert response reduces risk of security incidents and potential fines

- Estimated break-even: 18–20 months post Phase 3 delivery

- Alert auto-close of ~70% dramatically reduces noise and on-call fatigue

# 9. Approvals & Sign-Off

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Engineering Lead |  |  |  |
| Security & Compliance Lead |  |  |  |
| FinOps / Budget Owner |  |  |  |
| Programme / Project Manager |  |  |  |

Document prepared for funding approval. For questions or clarifications, please contact the D&A DLC Platform Team.